## Sheet1
ID | Task Name | Duration (Week) | Start (dd/mm/yyyy) | Finish (dd/mm/yyyy) | Week
[5 empty] | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Analysis
1 | Review previous work | 2 | 2021-09-20 | 2021-10-03 | bar: Week 5 to Week 6
2 | Define project scope | 1 | 2021-10-04 | 2021-10-10 | bar: Week 7
3 | Define project objective | 1 | 2021-10-04 | 2021-10-10 | bar: Week 7
4 | Gathering user requirement | 1 | 2021-10-04 | 2021-10-10 | bar: Week 7
Design
5 | Design system architecture | 2 | 2021-10-11 | 2021-10-24 | bar: Week 8 to Week 9
6 | Identify development tools | 2 | 2021-10-11 | 2021-10-24 | bar: Week 8 to Week 9
Implementations
7 | Coding | 3 | 2021-10-25 | 2021-11-14 | bar: Week 10 to Week 12
8 | Testing | 1 | 2021-11-15 | 2021-11-21 | bar: Week 13
9 | Maintaining | 2 | 2021-11-25 | 2021-12-05 | bar: Week 14 to Week 15
10 | Documentations | 1 | 2002-12-06 | 2021-12-12 | bar: Week 16